## Read Me
Employment and Training Contract Monitoring Tracker
State fiscal year 2026 (July 1, 2025, to June 30, 2026). Sample data. All names, organizations, and figures are fictional.
Sheet | What it holds
Scorecard | Pick a contractor in the yellow cell to see its measures by quarter, spending, deliverables, site visit results, corrective action status, and overall rating. The chart updates with the selection.
Portfolio Summary | One row per contract with spending, results against targets, compliance counts, and the overall rating. The as-of date used for overdue calculations is set here.
Contracts | Contract register: provider, program, service area, amount, term, and assigned monitor.
Targets | Annual targets for each contract and measure.
Measures | Quarterly results reported by each contractor, as a numerator and denominator, with the actual value, quarterly target, percent of target, and status calculated.
Annual Results | Year-to-date results by contract and measure, calculated from the Measures sheet.
Invoices | Quarterly invoices with the amount approved and any disallowed costs.
Deliverables | Required reports and plans with due and submitted dates. Status and days late calculate from the as-of date.
Site Visits | Findings and observations from monitoring visits, including file review results.
Corrective Actions | Corrective action plan items with due dates and status. Days overdue calculate from the as-of date.
Status rule | A measure is Met at 100 percent of target or more, Near at 90 to 99 percent, and Not met below 90 percent.
Rating rule | Corrective action required: fewer than 4 of 8 measures met or near, any overdue corrective action item, or disallowed costs above 1 percent of approved costs. Needs improvement: fewer than 6 measures met or near, or any open corrective action item. Otherwise Meets expectations.
Cell colors | Yellow cells are inputs. Blue text is entered data. Black text is calculated.

## Scorecard
Contractor Scorecard
Choose a provider in the yellow cell. Every figure on this sheet recalculates from the data sheets. Sample data. All names, organizations, and figures are fictional.
Provider |  | Kestrel Employment Services
Contract ID |  | LDHS-ET-26-017
Program |  | TANF and SNAP Employment and Training
Service area |  | Port Calder and Redfern counties
Contract amount |  | 1980000
Overall rating |  | Corrective action required
Performance measures
Measure ID | Measure | Q1 | Q2 | Q3 | Q4 | Year | Annual target | Percent of target | Status
M1 | Participants enrolled | 184 | 174 | 193 | 206 | 757 | 780 | 97.05% | Near
M2 | Assessed within 30 days of referral | 80.43% | 79.89% | 80.83% | 76.21% | 79.26% | 90% | 88.07% | Not met
M3 | Engaged in a work activity each month | 70.54% | 66.76% | 64.52% | 59.82% | 65.2% | 70% | 93.15% | Near
M4 | Job placements | 73 | 72 | 71 | 78 | 294 | 330 | 89.09% | Not met
M5 | Average starting wage | 14.8437 | 14.9646 | 14.7458 | 15.0821 | 14.9129 | 14.5 | 102.8% | Met
M6 | Employed 90 days after placement | 72.41% | 76.81% | 82.35% | 74.63% | 76.72% | 75% | 102.3% | Met
M7 | Credential earned by training completers | 60% | 60.53% | 61.9% | 60% | 60.61% | 60% | 101% | Met
M8 | Monthly reports submitted on time | 100% | 100% | 100% | 66.67% | 91.67% | 100% | 91.67% | Near
Spending |  |  |  |  | Compliance
Amount invoiced |  | 1924500 |  |  | Deliverables on time |  |  | 3
Amount approved |  | 1906100 |  |  | Deliverables late |  |  | 2
Disallowed costs |  | 18400 |  |  | Deliverables overdue |  |  | 1
Percent of contract paid |  | 96.27% |  |  | Site visit findings |  |  | 3
Cost per job placement |  | 6483.3333 |  |  | Open corrective action items |  |  | 2
Percent of placement target reached |  | 89.09% |  |  | Overdue corrective action items |  |  | 1
Measures met or near |  | 6
Chart data
Quarter | Job placements | Quarterly target
Q1 | 73 | 82.5
Q2 | 72 | 82.5
Q3 | 71 | 82.5
Q4 | 78 | 82.5

## Portfolio Summary
Portfolio Summary: Employment and Training Contracts, SFY 2026
Sample data. All names, organizations, and figures are fictional.
As-of date |  | 2026-08-15 | Input: used for overdue calculations on the Deliverables and Corrective Actions sheets
Provider | Contract ID | Contract amount | Approved to date | Percent paid | Job placements | Placement target | Percent of placement target | Measures met | Measures near | Deliverables late or overdue | Open CAP items | Overdue CAP items | Disallowed costs | Rating
Ridgeline Career Partners | LDHS-ET-26-011 | 2350000 | 2197300 | 93.5% | 454 | 420 | 108.1% | 6 | 2 | 0 | 0 | 0 | 0 | Meets expectations
Larch Valley Community Action | LDHS-ET-26-014 | 640000 | 599750 | 93.71% | 106 | 150 | 70.67% | 0 | 5 | 3 | 1 | 0 | 1850 | Needs improvement
Kestrel Employment Services | LDHS-ET-26-017 | 1980000 | 1906100 | 96.27% | 294 | 330 | 89.09% | 3 | 3 | 3 | 2 | 1 | 18400 | Corrective action required
Fenwick Adult Learning Center | LDHS-ET-26-022 | 720000 | 619200 | 86% | 108 | 110 | 98.18% | 6 | 2 | 0 | 0 | 0 | 0 | Meets expectations
All contracts |  | 5690000 | 5322350 | 93.54% | 962 | 1010 | 95.25% |  |  | 6 | 3 | 1 | 20250
Note on C4: Input. Date used to decide whether deliverables and corrective action items are overdue.

## Contracts
Contract Register
Sample data. All names, organizations, and figures are fictional.
Contract ID | Provider | Program | Service area | Contract amount | Start date | End date | Monitor ID
LDHS-ET-26-011 | Ridgeline Career Partners | TANF employment services | Bramwell and Northgate counties | 2350000 | 2025-07-01 | 2026-06-30 | CM-02
LDHS-ET-26-014 | Larch Valley Community Action | SNAP Employment and Training | Ashgrove, Whitlow, Glenrock, and Fenwick counties | 640000 | 2025-07-01 | 2026-06-30 | CM-01
LDHS-ET-26-017 | Kestrel Employment Services | TANF and SNAP Employment and Training | Port Calder and Redfern counties | 1980000 | 2025-07-01 | 2026-06-30 | CM-03
LDHS-ET-26-022 | Fenwick Adult Learning Center | SNAP Employment and Training (education and training) | Millbrook, Oakhurst, and Kessler counties | 720000 | 2025-07-01 | 2026-06-30 | CM-01

## Targets
Annual Targets
Count targets are annual; quarterly targets are one quarter of the annual target. Sample data. All names, organizations, and figures are fictional.
Contract ID | Measure ID | Measure | Type | Annual target
LDHS-ET-26-011 | M1 | Participants enrolled | Count | 900
LDHS-ET-26-011 | M2 | Assessed within 30 days of referral | Percent | 90%
LDHS-ET-26-011 | M3 | Engaged in a work activity each month | Percent | 70%
LDHS-ET-26-011 | M4 | Job placements | Count | 420
LDHS-ET-26-011 | M5 | Average starting wage | Dollar | 14.5
LDHS-ET-26-011 | M6 | Employed 90 days after placement | Percent | 75%
LDHS-ET-26-011 | M7 | Credential earned by training completers | Percent | 60%
LDHS-ET-26-011 | M8 | Monthly reports submitted on time | Percent | 100%
LDHS-ET-26-014 | M1 | Participants enrolled | Count | 360
LDHS-ET-26-014 | M2 | Assessed within 30 days of referral | Percent | 90%
LDHS-ET-26-014 | M3 | Engaged in a work activity each month | Percent | 70%
LDHS-ET-26-014 | M4 | Job placements | Count | 150
LDHS-ET-26-014 | M5 | Average starting wage | Dollar | 14.5
LDHS-ET-26-014 | M6 | Employed 90 days after placement | Percent | 75%
LDHS-ET-26-014 | M7 | Credential earned by training completers | Percent | 60%
LDHS-ET-26-014 | M8 | Monthly reports submitted on time | Percent | 100%
LDHS-ET-26-017 | M1 | Participants enrolled | Count | 780
LDHS-ET-26-017 | M2 | Assessed within 30 days of referral | Percent | 90%
LDHS-ET-26-017 | M3 | Engaged in a work activity each month | Percent | 70%
LDHS-ET-26-017 | M4 | Job placements | Count | 330
LDHS-ET-26-017 | M5 | Average starting wage | Dollar | 14.5
LDHS-ET-26-017 | M6 | Employed 90 days after placement | Percent | 75%
LDHS-ET-26-017 | M7 | Credential earned by training completers | Percent | 60%
LDHS-ET-26-017 | M8 | Monthly reports submitted on time | Percent | 100%
LDHS-ET-26-022 | M1 | Participants enrolled | Count | 300
LDHS-ET-26-022 | M2 | Assessed within 30 days of referral | Percent | 90%
LDHS-ET-26-022 | M3 | Engaged in a work activity each month | Percent | 70%
LDHS-ET-26-022 | M4 | Job placements | Count | 110
LDHS-ET-26-022 | M5 | Average starting wage | Dollar | 14.5
LDHS-ET-26-022 | M6 | Employed 90 days after placement | Percent | 75%
LDHS-ET-26-022 | M7 | Credential earned by training completers | Percent | 60%
LDHS-ET-26-022 | M8 | Monthly reports submitted on time | Percent | 100%

## Measures
Quarterly Performance Measures
Contractors report a numerator and denominator for each rate. Counts have no denominator. Sample data. All names, organizations, and figures are fictional.
Contract ID | Measure ID | Measure | Quarter | Numerator | Denominator | Actual | Quarterly target | Percent of target | Status
LDHS-ET-26-011 | M1 | Participants enrolled | Q1 | 237 |  | 237 | 225 | 105.3% | Met
LDHS-ET-26-011 | M2 | Assessed within 30 days of referral | Q1 | 224 | 237 | 94.51% | 90% | 105% | Met
LDHS-ET-26-011 | M3 | Engaged in a work activity each month | Q1 | 361 | 490 | 73.67% | 70% | 105.2% | Met
LDHS-ET-26-011 | M4 | Job placements | Q1 | 109 |  | 109 | 105 | 103.8% | Met
LDHS-ET-26-011 | M5 | Average starting wage | Q1 | 1699.66 | 109 | 15.5932 | 14.5 | 107.5% | Met
LDHS-ET-26-011 | M6 | Employed 90 days after placement | Q1 | 62 | 87 | 71.26% | 75% | 95.02% | Near
LDHS-ET-26-011 | M7 | Credential earned by training completers | Q1 | 31 | 52 | 59.62% | 60% | 99.36% | Near
LDHS-ET-26-011 | M8 | Monthly reports submitted on time | Q1 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-011 | M1 | Participants enrolled | Q2 | 207 |  | 207 | 225 | 92% | Near
LDHS-ET-26-011 | M2 | Assessed within 30 days of referral | Q2 | 195 | 207 | 94.2% | 90% | 104.7% | Met
LDHS-ET-26-011 | M3 | Engaged in a work activity each month | Q2 | 309 | 433 | 71.36% | 70% | 101.9% | Met
LDHS-ET-26-011 | M4 | Job placements | Q2 | 115 |  | 115 | 105 | 109.5% | Met
LDHS-ET-26-011 | M5 | Average starting wage | Q2 | 1800.91 | 115 | 15.6601 | 14.5 | 108% | Met
LDHS-ET-26-011 | M6 | Employed 90 days after placement | Q2 | 79 | 103 | 76.7% | 75% | 102.3% | Met
LDHS-ET-26-011 | M7 | Credential earned by training completers | Q2 | 27 | 45 | 60% | 60% | 100% | Met
LDHS-ET-26-011 | M8 | Monthly reports submitted on time | Q2 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-011 | M1 | Participants enrolled | Q3 | 240 |  | 240 | 225 | 106.7% | Met
LDHS-ET-26-011 | M2 | Assessed within 30 days of referral | Q3 | 229 | 240 | 95.42% | 90% | 106% | Met
LDHS-ET-26-011 | M3 | Engaged in a work activity each month | Q3 | 368 | 514 | 71.6% | 70% | 102.3% | Met
LDHS-ET-26-011 | M4 | Job placements | Q3 | 108 |  | 108 | 105 | 102.9% | Met
LDHS-ET-26-011 | M5 | Average starting wage | Q3 | 1639.04 | 108 | 15.1763 | 14.5 | 104.7% | Met
LDHS-ET-26-011 | M6 | Employed 90 days after placement | Q3 | 77 | 109 | 70.64% | 75% | 94.19% | Near
LDHS-ET-26-011 | M7 | Credential earned by training completers | Q3 | 30 | 52 | 57.69% | 60% | 96.15% | Near
LDHS-ET-26-011 | M8 | Monthly reports submitted on time | Q3 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-011 | M1 | Participants enrolled | Q4 | 252 |  | 252 | 225 | 112% | Met
LDHS-ET-26-011 | M2 | Assessed within 30 days of referral | Q4 | 234 | 252 | 92.86% | 90% | 103.2% | Met
LDHS-ET-26-011 | M3 | Engaged in a work activity each month | Q4 | 347 | 500 | 69.4% | 70% | 99.14% | Near
LDHS-ET-26-011 | M4 | Job placements | Q4 | 122 |  | 122 | 105 | 116.2% | Met
LDHS-ET-26-011 | M5 | Average starting wage | Q4 | 1795.94 | 122 | 14.7208 | 14.5 | 101.5% | Met
LDHS-ET-26-011 | M6 | Employed 90 days after placement | Q4 | 73 | 102 | 71.57% | 75% | 95.42% | Near
LDHS-ET-26-011 | M7 | Credential earned by training completers | Q4 | 33 | 55 | 60% | 60% | 100% | Met
LDHS-ET-26-011 | M8 | Monthly reports submitted on time | Q4 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-014 | M1 | Participants enrolled | Q1 | 80 |  | 80 | 90 | 88.89% | Not met
LDHS-ET-26-014 | M2 | Assessed within 30 days of referral | Q1 | 68 | 80 | 85% | 90% | 94.44% | Near
LDHS-ET-26-014 | M3 | Engaged in a work activity each month | Q1 | 122 | 193 | 63.21% | 70% | 90.3% | Near
LDHS-ET-26-014 | M4 | Job placements | Q1 | 27 |  | 27 | 37.5 | 72% | Not met
LDHS-ET-26-014 | M5 | Average starting wage | Q1 | 353.31 | 27 | 13.0856 | 14.5 | 90.25% | Near
LDHS-ET-26-014 | M6 | Employed 90 days after placement | Q1 | 14 | 21 | 66.67% | 75% | 88.89% | Not met
LDHS-ET-26-014 | M7 | Credential earned by training completers | Q1 | 9 | 17 | 52.94% | 60% | 88.24% | Not met
LDHS-ET-26-014 | M8 | Monthly reports submitted on time | Q1 | 2 | 3 | 66.67% | 100% | 66.67% | Not met
LDHS-ET-26-014 | M1 | Participants enrolled | Q2 | 65 |  | 65 | 90 | 72.22% | Not met
LDHS-ET-26-014 | M2 | Assessed within 30 days of referral | Q2 | 53 | 65 | 81.54% | 90% | 90.6% | Near
LDHS-ET-26-014 | M3 | Engaged in a work activity each month | Q2 | 106 | 174 | 60.92% | 70% | 87.03% | Not met
LDHS-ET-26-014 | M4 | Job placements | Q2 | 27 |  | 27 | 37.5 | 72% | Not met
LDHS-ET-26-014 | M5 | Average starting wage | Q2 | 352.16 | 27 | 13.043 | 14.5 | 89.95% | Not met
LDHS-ET-26-014 | M6 | Employed 90 days after placement | Q2 | 18 | 25 | 72% | 75% | 96% | Near
LDHS-ET-26-014 | M7 | Credential earned by training completers | Q2 | 7 | 14 | 50% | 60% | 83.33% | Not met
LDHS-ET-26-014 | M8 | Monthly reports submitted on time | Q2 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-014 | M1 | Participants enrolled | Q3 | 72 |  | 72 | 90 | 80% | Not met
LDHS-ET-26-014 | M2 | Assessed within 30 days of referral | Q3 | 62 | 72 | 86.11% | 90% | 95.68% | Near
LDHS-ET-26-014 | M3 | Engaged in a work activity each month | Q3 | 126 | 184 | 68.48% | 70% | 97.83% | Near
LDHS-ET-26-014 | M4 | Job placements | Q3 | 25 |  | 25 | 37.5 | 66.67% | Not met
LDHS-ET-26-014 | M5 | Average starting wage | Q3 | 337.56 | 25 | 13.5024 | 14.5 | 93.12% | Near
LDHS-ET-26-014 | M6 | Employed 90 days after placement | Q3 | 19 | 25 | 76% | 75% | 101.3% | Met
LDHS-ET-26-014 | M7 | Credential earned by training completers | Q3 | 9 | 15 | 60% | 60% | 100% | Met
LDHS-ET-26-014 | M8 | Monthly reports submitted on time | Q3 | 2 | 3 | 66.67% | 100% | 66.67% | Not met
LDHS-ET-26-014 | M1 | Participants enrolled | Q4 | 78 |  | 78 | 90 | 86.67% | Not met
LDHS-ET-26-014 | M2 | Assessed within 30 days of referral | Q4 | 66 | 78 | 84.62% | 90% | 94.02% | Near
LDHS-ET-26-014 | M3 | Engaged in a work activity each month | Q4 | 128 | 186 | 68.82% | 70% | 98.31% | Near
LDHS-ET-26-014 | M4 | Job placements | Q4 | 27 |  | 27 | 37.5 | 72% | Not met
LDHS-ET-26-014 | M5 | Average starting wage | Q4 | 361.29 | 27 | 13.3811 | 14.5 | 92.28% | Near
LDHS-ET-26-014 | M6 | Employed 90 days after placement | Q4 | 17 | 23 | 73.91% | 75% | 98.55% | Near
LDHS-ET-26-014 | M7 | Credential earned by training completers | Q4 | 10 | 17 | 58.82% | 60% | 98.04% | Near
LDHS-ET-26-014 | M8 | Monthly reports submitted on time | Q4 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-017 | M1 | Participants enrolled | Q1 | 184 |  | 184 | 195 | 94.36% | Near
LDHS-ET-26-017 | M2 | Assessed within 30 days of referral | Q1 | 148 | 184 | 80.43% | 90% | 89.37% | Not met
LDHS-ET-26-017 | M3 | Engaged in a work activity each month | Q1 | 273 | 387 | 70.54% | 70% | 100.8% | Met
LDHS-ET-26-017 | M4 | Job placements | Q1 | 73 |  | 73 | 82.5 | 88.48% | Not met
LDHS-ET-26-017 | M5 | Average starting wage | Q1 | 1083.59 | 73 | 14.8437 | 14.5 | 102.4% | Met
LDHS-ET-26-017 | M6 | Employed 90 days after placement | Q1 | 42 | 58 | 72.41% | 75% | 96.55% | Near
LDHS-ET-26-017 | M7 | Credential earned by training completers | Q1 | 24 | 40 | 60% | 60% | 100% | Met
LDHS-ET-26-017 | M8 | Monthly reports submitted on time | Q1 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-017 | M1 | Participants enrolled | Q2 | 174 |  | 174 | 195 | 89.23% | Not met
LDHS-ET-26-017 | M2 | Assessed within 30 days of referral | Q2 | 139 | 174 | 79.89% | 90% | 88.76% | Not met
LDHS-ET-26-017 | M3 | Engaged in a work activity each month | Q2 | 237 | 355 | 66.76% | 70% | 95.37% | Near
LDHS-ET-26-017 | M4 | Job placements | Q2 | 72 |  | 72 | 82.5 | 87.27% | Not met
LDHS-ET-26-017 | M5 | Average starting wage | Q2 | 1077.45 | 72 | 14.9646 | 14.5 | 103.2% | Met
LDHS-ET-26-017 | M6 | Employed 90 days after placement | Q2 | 53 | 69 | 76.81% | 75% | 102.4% | Met
LDHS-ET-26-017 | M7 | Credential earned by training completers | Q2 | 23 | 38 | 60.53% | 60% | 100.9% | Met
LDHS-ET-26-017 | M8 | Monthly reports submitted on time | Q2 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-017 | M1 | Participants enrolled | Q3 | 193 |  | 193 | 195 | 98.97% | Near
LDHS-ET-26-017 | M2 | Assessed within 30 days of referral | Q3 | 156 | 193 | 80.83% | 90% | 89.81% | Not met
LDHS-ET-26-017 | M3 | Engaged in a work activity each month | Q3 | 271 | 420 | 64.52% | 70% | 92.18% | Near
LDHS-ET-26-017 | M4 | Job placements | Q3 | 71 |  | 71 | 82.5 | 86.06% | Not met
LDHS-ET-26-017 | M5 | Average starting wage | Q3 | 1046.95 | 71 | 14.7458 | 14.5 | 101.7% | Met
LDHS-ET-26-017 | M6 | Employed 90 days after placement | Q3 | 56 | 68 | 82.35% | 75% | 109.8% | Met
LDHS-ET-26-017 | M7 | Credential earned by training completers | Q3 | 26 | 42 | 61.9% | 60% | 103.2% | Met
LDHS-ET-26-017 | M8 | Monthly reports submitted on time | Q3 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-017 | M1 | Participants enrolled | Q4 | 206 |  | 206 | 195 | 105.6% | Met
LDHS-ET-26-017 | M2 | Assessed within 30 days of referral | Q4 | 157 | 206 | 76.21% | 90% | 84.68% | Not met
LDHS-ET-26-017 | M3 | Engaged in a work activity each month | Q4 | 259 | 433 | 59.82% | 70% | 85.45% | Not met
LDHS-ET-26-017 | M4 | Job placements | Q4 | 78 |  | 78 | 82.5 | 94.55% | Near
LDHS-ET-26-017 | M5 | Average starting wage | Q4 | 1176.4 | 78 | 15.0821 | 14.5 | 104% | Met
LDHS-ET-26-017 | M6 | Employed 90 days after placement | Q4 | 50 | 67 | 74.63% | 75% | 99.5% | Near
LDHS-ET-26-017 | M7 | Credential earned by training completers | Q4 | 27 | 45 | 60% | 60% | 100% | Met
LDHS-ET-26-017 | M8 | Monthly reports submitted on time | Q4 | 2 | 3 | 66.67% | 100% | 66.67% | Not met
LDHS-ET-26-022 | M1 | Participants enrolled | Q1 | 40 |  | 40 | 75 | 53.33% | Not met
LDHS-ET-26-022 | M2 | Assessed within 30 days of referral | Q1 | 38 | 40 | 95% | 90% | 105.6% | Met
LDHS-ET-26-022 | M3 | Engaged in a work activity each month | Q1 | 71 | 99 | 71.72% | 70% | 102.5% | Met
LDHS-ET-26-022 | M4 | Job placements | Q1 | 15 |  | 15 | 27.5 | 54.55% | Not met
LDHS-ET-26-022 | M5 | Average starting wage | Q1 | 230.97 | 15 | 15.398 | 14.5 | 106.2% | Met
LDHS-ET-26-022 | M6 | Employed 90 days after placement | Q1 | 9 | 12 | 75% | 75% | 100% | Met
LDHS-ET-26-022 | M7 | Credential earned by training completers | Q1 | 6 | 8 | 75% | 60% | 125% | Met
LDHS-ET-26-022 | M8 | Monthly reports submitted on time | Q1 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-022 | M1 | Participants enrolled | Q2 | 60 |  | 60 | 75 | 80% | Not met
LDHS-ET-26-022 | M2 | Assessed within 30 days of referral | Q2 | 58 | 60 | 96.67% | 90% | 107.4% | Met
LDHS-ET-26-022 | M3 | Engaged in a work activity each month | Q2 | 113 | 147 | 76.87% | 70% | 109.8% | Met
LDHS-ET-26-022 | M4 | Job placements | Q2 | 22 |  | 22 | 27.5 | 80% | Not met
LDHS-ET-26-022 | M5 | Average starting wage | Q2 | 334.48 | 22 | 15.2036 | 14.5 | 104.9% | Met
LDHS-ET-26-022 | M6 | Employed 90 days after placement | Q2 | 11 | 14 | 78.57% | 75% | 104.8% | Met
LDHS-ET-26-022 | M7 | Credential earned by training completers | Q2 | 9 | 13 | 69.23% | 60% | 115.4% | Met
LDHS-ET-26-022 | M8 | Monthly reports submitted on time | Q2 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-022 | M1 | Participants enrolled | Q3 | 86 |  | 86 | 75 | 114.7% | Met
LDHS-ET-26-022 | M2 | Assessed within 30 days of referral | Q3 | 79 | 86 | 91.86% | 90% | 102.1% | Met
LDHS-ET-26-022 | M3 | Engaged in a work activity each month | Q3 | 158 | 222 | 71.17% | 70% | 101.7% | Met
LDHS-ET-26-022 | M4 | Job placements | Q3 | 33 |  | 33 | 27.5 | 120% | Met
LDHS-ET-26-022 | M5 | Average starting wage | Q3 | 492.17 | 33 | 14.9142 | 14.5 | 102.9% | Met
LDHS-ET-26-022 | M6 | Employed 90 days after placement | Q3 | 16 | 20 | 80% | 75% | 106.7% | Met
LDHS-ET-26-022 | M7 | Credential earned by training completers | Q3 | 12 | 18 | 66.67% | 60% | 111.1% | Met
LDHS-ET-26-022 | M8 | Monthly reports submitted on time | Q3 | 3 | 3 | 100% | 100% | 100% | Met
LDHS-ET-26-022 | M1 | Participants enrolled | Q4 | 99 |  | 99 | 75 | 132% | Met
LDHS-ET-26-022 | M2 | Assessed within 30 days of referral | Q4 | 95 | 99 | 95.96% | 90% | 106.6% | Met
LDHS-ET-26-022 | M3 | Engaged in a work activity each month | Q4 | 163 | 235 | 69.36% | 70% | 99.09% | Near
LDHS-ET-26-022 | M4 | Job placements | Q4 | 38 |  | 38 | 27.5 | 138.2% | Met
LDHS-ET-26-022 | M5 | Average starting wage | Q4 | 563.16 | 38 | 14.82 | 14.5 | 102.2% | Met
LDHS-ET-26-022 | M6 | Employed 90 days after placement | Q4 | 24 | 31 | 77.42% | 75% | 103.2% | Met
LDHS-ET-26-022 | M7 | Credential earned by training completers | Q4 | 15 | 21 | 71.43% | 60% | 119% | Met
LDHS-ET-26-022 | M8 | Monthly reports submitted on time | Q4 | 3 | 3 | 100% | 100% | 100% | Met

## Annual Results
Annual Results by Contract and Measure
Year-to-date results through Quarter 4, calculated from the Measures sheet. Sample data. All names, organizations, and figures are fictional.
Contract ID | Measure ID | Measure | Type | Year to date | Annual target | Percent of target | Status
LDHS-ET-26-011 | M1 | Participants enrolled | Count | 936 | 900 | 104% | Met
LDHS-ET-26-011 | M2 | Assessed within 30 days of referral | Percent | 94.23% | 90% | 104.7% | Met
LDHS-ET-26-011 | M3 | Engaged in a work activity each month | Percent | 71.5% | 70% | 102.1% | Met
LDHS-ET-26-011 | M4 | Job placements | Count | 454 | 420 | 108.1% | Met
LDHS-ET-26-011 | M5 | Average starting wage | Dollar | 15.2765 | 14.5 | 105.4% | Met
LDHS-ET-26-011 | M6 | Employed 90 days after placement | Percent | 72.57% | 75% | 96.76% | Near
LDHS-ET-26-011 | M7 | Credential earned by training completers | Percent | 59.31% | 60% | 98.86% | Near
LDHS-ET-26-011 | M8 | Monthly reports submitted on time | Percent | 100% | 100% | 100% | Met
LDHS-ET-26-014 | M1 | Participants enrolled | Count | 295 | 360 | 81.94% | Not met
LDHS-ET-26-014 | M2 | Assessed within 30 days of referral | Percent | 84.41% | 90% | 93.79% | Near
LDHS-ET-26-014 | M3 | Engaged in a work activity each month | Percent | 65.4% | 70% | 93.43% | Near
LDHS-ET-26-014 | M4 | Job placements | Count | 106 | 150 | 70.67% | Not met
LDHS-ET-26-014 | M5 | Average starting wage | Dollar | 13.2483 | 14.5 | 91.37% | Near
LDHS-ET-26-014 | M6 | Employed 90 days after placement | Percent | 72.34% | 75% | 96.45% | Near
LDHS-ET-26-014 | M7 | Credential earned by training completers | Percent | 55.56% | 60% | 92.59% | Near
LDHS-ET-26-014 | M8 | Monthly reports submitted on time | Percent | 83.33% | 100% | 83.33% | Not met
LDHS-ET-26-017 | M1 | Participants enrolled | Count | 757 | 780 | 97.05% | Near
LDHS-ET-26-017 | M2 | Assessed within 30 days of referral | Percent | 79.26% | 90% | 88.07% | Not met
LDHS-ET-26-017 | M3 | Engaged in a work activity each month | Percent | 65.2% | 70% | 93.15% | Near
LDHS-ET-26-017 | M4 | Job placements | Count | 294 | 330 | 89.09% | Not met
LDHS-ET-26-017 | M5 | Average starting wage | Dollar | 14.9129 | 14.5 | 102.8% | Met
LDHS-ET-26-017 | M6 | Employed 90 days after placement | Percent | 76.72% | 75% | 102.3% | Met
LDHS-ET-26-017 | M7 | Credential earned by training completers | Percent | 60.61% | 60% | 101% | Met
LDHS-ET-26-017 | M8 | Monthly reports submitted on time | Percent | 91.67% | 100% | 91.67% | Near
LDHS-ET-26-022 | M1 | Participants enrolled | Count | 285 | 300 | 95% | Near
LDHS-ET-26-022 | M2 | Assessed within 30 days of referral | Percent | 94.74% | 90% | 105.3% | Met
LDHS-ET-26-022 | M3 | Engaged in a work activity each month | Percent | 71.83% | 70% | 102.6% | Met
LDHS-ET-26-022 | M4 | Job placements | Count | 108 | 110 | 98.18% | Near
LDHS-ET-26-022 | M5 | Average starting wage | Dollar | 15.0072 | 14.5 | 103.5% | Met
LDHS-ET-26-022 | M6 | Employed 90 days after placement | Percent | 77.92% | 75% | 103.9% | Met
LDHS-ET-26-022 | M7 | Credential earned by training completers | Percent | 70% | 60% | 116.7% | Met
LDHS-ET-26-022 | M8 | Monthly reports submitted on time | Percent | 100% | 100% | 100% | Met

## Invoices
Quarterly Invoices
Disallowed costs are the difference between the amount invoiced and the amount approved. Sample data. All names, organizations, and figures are fictional.
Contract ID | Quarter | Date submitted | Amount invoiced | Amount approved | Disallowed | Note
LDHS-ET-26-011 | Q1 | 2025-10-20 | 505400 | 505400 | 0
LDHS-ET-26-011 | Q2 | 2026-01-21 | 549300 | 549300 | 0
LDHS-ET-26-011 | Q3 | 2026-04-22 | 571300 | 571300 | 0
LDHS-ET-26-011 | Q4 | 2026-07-24 | 571300 | 571300 | 0
LDHS-ET-26-014 | Q1 | 2025-10-20 | 138400 | 138400 | 0
LDHS-ET-26-014 | Q2 | 2026-02-27 | 150400 | 150400 | 0
LDHS-ET-26-014 | Q3 | 2026-05-15 | 156400 | 154550 | 1850 | Staff time charged to another program
LDHS-ET-26-014 | Q4 | 2026-07-24 | 156400 | 156400 | 0
LDHS-ET-26-017 | Q1 | 2025-10-20 | 442600 | 442600 | 0
LDHS-ET-26-017 | Q2 | 2026-01-21 | 481100 | 469900 | 11200 | Supportive service payments without receipts
LDHS-ET-26-017 | Q3 | 2026-04-22 | 500400 | 493200 | 7200 | Supportive service payments without receipts
LDHS-ET-26-017 | Q4 | 2026-07-24 | 500400 | 500400 | 0
LDHS-ET-26-022 | Q1 | 2025-10-20 | 105300 | 105300 | 0
LDHS-ET-26-022 | Q2 | 2026-01-21 | 142400 | 142400 | 0
LDHS-ET-26-022 | Q3 | 2026-04-22 | 173400 | 173400 | 0
LDHS-ET-26-022 | Q4 | 2026-07-24 | 198100 | 198100 | 0

## Deliverables
Contract Deliverables
Status and days late use the as-of date on the Portfolio Summary sheet. Sample data. All names, organizations, and figures are fictional.
Contract ID | Deliverable | Due date | Date submitted | Status | Days late
LDHS-ET-26-011 | Staffing plan update | 2025-08-15 | 2025-08-12 | On time | 0
LDHS-ET-26-011 | Quarter 1 program report | 2025-10-31 | 2025-10-29 | On time | 0
LDHS-ET-26-011 | Quarter 2 program report | 2026-01-31 | 2026-01-28 | On time | 0
LDHS-ET-26-011 | Quarter 3 program report | 2026-04-30 | 2026-04-27 | On time | 0
LDHS-ET-26-011 | Participant survey summary | 2026-06-30 | 2026-06-26 | On time | 0
LDHS-ET-26-011 | Quarter 4 program report | 2026-07-31 | 2026-07-30 | On time | 0
LDHS-ET-26-014 | Staffing plan update | 2025-08-15 | 2025-08-14 | On time | 0
LDHS-ET-26-014 | Quarter 1 program report | 2025-10-31 | 2025-11-12 | Late | 12
LDHS-ET-26-014 | Quarter 2 program report | 2026-01-31 | 2026-01-30 | On time | 0
LDHS-ET-26-014 | Quarter 3 program report | 2026-04-30 | 2026-05-19 | Late | 19
LDHS-ET-26-014 | Participant survey summary | 2026-06-30 | 2026-07-08 | Late | 8
LDHS-ET-26-014 | Quarter 4 program report | 2026-07-31 | 2026-07-31 | On time | 0
LDHS-ET-26-017 | Staffing plan update | 2025-08-15 | 2025-08-20 | Late | 5
LDHS-ET-26-017 | Quarter 1 program report | 2025-10-31 | 2025-10-31 | On time | 0
LDHS-ET-26-017 | Quarter 2 program report | 2026-01-31 | 2026-02-06 | Late | 6
LDHS-ET-26-017 | Quarter 3 program report | 2026-04-30 | 2026-04-30 | On time | 0
LDHS-ET-26-017 | Participant survey summary | 2026-06-30 | 2026-06-30 | On time | 0
LDHS-ET-26-017 | Quarter 4 program report | 2026-07-31 |  | Overdue | 15
LDHS-ET-26-022 | Staffing plan update | 2025-08-15 | 2025-08-01 | On time | 0
LDHS-ET-26-022 | Quarter 1 program report | 2025-10-31 | 2025-10-24 | On time | 0
LDHS-ET-26-022 | Quarter 2 program report | 2026-01-31 | 2026-01-26 | On time | 0
LDHS-ET-26-022 | Quarter 3 program report | 2026-04-30 | 2026-04-24 | On time | 0
LDHS-ET-26-022 | Participant survey summary | 2026-06-30 | 2026-06-22 | On time | 0
LDHS-ET-26-022 | Quarter 4 program report | 2026-07-31 | 2026-07-28 | On time | 0

## Site Visits
Site Visit Findings
File reviews use a random sample of participant files at each visit. Sample data. All names, organizations, and figures are fictional.
Contract ID | Visit date | Files reviewed | Area | Finding or observation | Type | Corrective action required
LDHS-ET-26-011 | 2026-03-10 | 20 | Employment plan | Employment plans in 2 of 20 files were signed but not dated. | Observation | No
LDHS-ET-26-014 | 2026-02-18 | 20 | Attendance verification | Training attendance was not verified against sign-in sheets in 5 of 20 files. | Finding | Yes
LDHS-ET-26-014 | 2026-02-18 | 20 | Assessment timeliness | Initial assessment was completed after 30 days in 4 of 20 files. | Finding | Yes
LDHS-ET-26-017 | 2026-01-21 | 20 | Eligibility documentation | Referral and eligibility documents were missing in 6 of 20 files. | Finding | Yes
LDHS-ET-26-017 | 2026-01-21 | 20 | Supportive services | Supportive service payments of $18,400 had no receipts or approvals on file. | Finding | Yes
LDHS-ET-26-017 | 2026-01-21 | 20 | Employment plan | Employment plans were not signed by the participant in 4 of 20 files. | Finding | Yes
LDHS-ET-26-017 | 2026-05-14 | 10 | Eligibility documentation | Follow-up visit: eligibility documents were complete in 9 of 10 new files. | Observation | No
LDHS-ET-26-022 | 2026-04-08 | 20 | Credential documentation | Credential copies were kept in instructor files instead of the participant file. | Observation | No

## Corrective Actions
Corrective Action Plan Items
Days overdue use the as-of date on the Portfolio Summary sheet. Sample data. All names, organizations, and figures are fictional.
CAP ID | Contract ID | Required action | Due date | Status | Date closed | Days overdue | Overdue
CAP-26-03 | LDHS-ET-26-014 | Verify training hours against sign-in sheets before reporting participation. | 2026-04-30 | Closed | 2026-04-22 | 0 | No
CAP-26-04 | LDHS-ET-26-014 | Complete initial assessments within 30 days and track them on a weekly log. | 2026-09-30 | In progress |  | 0 | No
CAP-26-01 | LDHS-ET-26-017 | Obtain missing referral and eligibility documents and add an intake checklist. | 2026-03-31 | Closed | 2026-03-27 | 0 | No
CAP-26-02 | LDHS-ET-26-017 | Repay or document $18,400 in supportive service payments and adopt a receipt policy. | 2026-06-30 | Open |  | 46 | Yes
CAP-26-05 | LDHS-ET-26-017 | Train case managers on participant signatures for employment plans. | 2026-08-31 | In progress |  | 0 | No

## Lists
Measure ID | Measure | Type | Counted as | CAP status | Quarter
M1 | Participants enrolled | Count | participants | Open | Q1
M2 | Assessed within 30 days of referral | Percent | of new enrollees | In progress | Q2
M3 | Engaged in a work activity each month | Percent | of active participants | Closed | Q3
M4 | Job placements | Count | placements |  | Q4
M5 | Average starting wage | Dollar | per hour
M6 | Employed 90 days after placement | Percent | of placements due for follow-up
M7 | Credential earned by training completers | Percent | of training completers
M8 | Monthly reports submitted on time | Percent | of monthly reports